## WA
Government of Nepal | Government of Nepal | Government of Nepal | Government of Nepal | Government of Nepal | Government of Nepal | Government of Nepal | Government of Nepal | Government of Nepal | Government of Nepal | Government of Nepal | Government of Nepal | Government of Nepal | Government of Nepal | Government of Nepal | Government of Nepal | Government of Nepal | Government of Nepal | Government of Nepal
Ministry of Physical Infrastructure and Transport | Ministry of Physical Infrastructure and Transport | Ministry of Physical Infrastructure and Transport | Ministry of Physical Infrastructure and Transport | Ministry of Physical Infrastructure and Transport | Ministry of Physical Infrastructure and Transport | Ministry of Physical Infrastructure and Transport | Ministry of Physical Infrastructure and Transport | Ministry of Physical Infrastructure and Transport | Ministry of Physical Infrastructure and Transport | Ministry of Physical Infrastructure and Transport | Ministry of Physical Infrastructure and Transport | Ministry of Physical Infrastructure and Transport | Ministry of Physical Infrastructure and Transport | Ministry of Physical Infrastructure and Transport | Ministry of Physical Infrastructure and Transport | Ministry of Physical Infrastructure and Transport | Ministry of Physical Infrastructure and Transport | Ministry of Physical Infrastructure and Transport
Department of Roads | Department of Roads | Department of Roads | Department of Roads | Department of Roads | Department of Roads | Department of Roads | Department of Roads | Department of Roads | Department of Roads | Department of Roads | Department of Roads | Department of Roads | Department of Roads | Department of Roads | Department of Roads | Department of Roads | Department of Roads | Department of Roads
Federal Road Supervision and Monitoring Office Pokhara | Federal Road Supervision and Monitoring Office Pokhara | Federal Road Supervision and Monitoring Office Pokhara | Federal Road Supervision and Monitoring Office Pokhara | Federal Road Supervision and Monitoring Office Pokhara | Federal Road Supervision and Monitoring Office Pokhara | Federal Road Supervision and Monitoring Office Pokhara | Federal Road Supervision and Monitoring Office Pokhara | Federal Road Supervision and Monitoring Office Pokhara | Federal Road Supervision and Monitoring Office Pokhara | Federal Road Supervision and Monitoring Office Pokhara | Federal Road Supervision and Monitoring Office Pokhara | Federal Road Supervision and Monitoring Office Pokhara | Federal Road Supervision and Monitoring Office Pokhara | Federal Road Supervision and Monitoring Office Pokhara | Federal Road Supervision and Monitoring Office Pokhara | Federal Road Supervision and Monitoring Office Pokhara | Federal Road Supervision and Monitoring Office Pokhara | Federal Road Supervision and Monitoring Office Pokhara
Road Division Pokhara | Road Division Pokhara | Road Division Pokhara | Road Division Pokhara | Road Division Pokhara | Road Division Pokhara | Road Division Pokhara | Road Division Pokhara | Road Division Pokhara | Road Division Pokhara | Road Division Pokhara | Road Division Pokhara | Road Division Pokhara | Road Division Pokhara | Road Division Pokhara | Road Division Pokhara | Road Division Pokhara | Road Division Pokhara | Road Division Pokhara
Kaski | Kaski | Kaski | Kaski | Kaski | Kaski | Kaski | Kaski | Kaski | Kaski | Kaski | Kaski | Kaski | Kaski | Kaski | Kaski | Kaski | Kaski | Kaski
Office Code No.:337713901
Work Acceptance Report
Name of Project: Road Improvement Works on Bhyakute Pandhera Shikhardanda-Thamdanda Dhnaubase Road, Galyang Municipality 11, Syangja | [9 empty] | Contract Identification No: RDPKR/33701017/080/81/17
Name Of Road: Bhyakute Pandhera Shikhardanda-Thamdanda Dhnaubase Road, Galyang Municipality 11, Syangja | [9 empty] | Name of Contractor: M/S Gejha Kalika Construction Pvt.Ltd,Galyang-3 Syangja
Total Estimated Amount (Without PS & VAT) |  | 0 |  |  | (Original) | 0 |  | (First Variation) |  | Agreement Date: 2081/07/26
Total Actual paid Amount (Without PS & VAT) |  | #REF! | [7 empty] | Date of Completion: 2082/02/20
% Increased or Decreased in amount wrt original etimated Amount: | [5 empty] | #REF! |  |  |  | Date of work Completed: 2080/01/14
% Increased or Decreased in amount wrt revised Estimated Amount: | [5 empty] | #REF! |  |  |  | Date of Report: 2081/01/14
S.N. | Description of Works | Unit | As per Original Estimate |  |  | Estimate As per variation-01 |  |  | Actual work done |  |  | Difference (with respect to Original Estimate) |  |  | Difference (with respect to Estimate after Variation) |  |  | Remarks
|  |  | Quantity | Rate | Amount | Quantity | Rate | Amount | Quantity | Rate | Amount | Quantity | Rate | Amount | Quantity | Rate | Amount
| 1 |  | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11=2-8 | 12=3-9 | 13=11*12 | 14=5-8 | 15=6-9 | 16=14*15 | 17
1 | General Works
1.1 | Relocation of services / minor infrastructures,Engineer's Facility, Office Accessories and equipment, Quality Control as per specifications and instruction of the Engineer.[111] | PS | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 200000 | 0 | 1 | -200000 | -200000 | 1 | -200000 | -200000
1.2 | Insurances for the loss of damage to works, plant, material, equipment, property and personnel injury or death and commission of bank security and performance guarantee all complete, as per specification (SS/SP-117) and instruction of Engineer. | Job | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 250000 | 0 | 1 | -250000 | -250000 | 1 | -250000 | -250000
2 | Earthwork |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | [5 empty] | -450000
2.1 | Roadway Excavation in all types of Soil by Mechanical Means as per Drawing and technical specifications including removal of stumps and other deleterious matter, all lifts and lead as per Drawing and instruction of the Engineer.[905] |  | 3000 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
0 | Sub-Total 2 |  | 50 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 50 | 0 | 0 | 0 | 0 | 0
3 | Structural Works | 0 | 0 | 0 | 0 | 364.61 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 364.61 | 0 | 0
3.1 | Excavation for Structures Foundation, Earth work in excavation of foundation of structures, including construction of shoring and bracing, removal of stumps and other deleterious matter & Backfilling with Suitable Material as per Drawing and Technical Specifications.,[907] | Cum | 443.18 | 0 | 0 | 118.93 | 0 | 0 | 0 | 7000 | 0 | 443.18 | -7000 | -3102260 | 118.93 | -7000 | -832510
3.2 | Providing and laying of hand pack Stone soling with 150 to 200 mm thick stones and packing with smaller stone on prepared surface as per Drawing and Technical Specifications.[1006] | Cum | 158.95 | 0 | 0 | 8.88 | 0 | 0 | 0 | 6250 | 0 | 158.95 | -6250 | -993437.5 | 8.88 | -6250 | -55500
3.3 | Providing and laying of Plain/Reinforced Cement Concrete in Foundation complete as per Drawing and Technical Specifications, PCC Grade M 15 including formworks all complete.[2000] | Cum | 2.16 | 0 | 0 | 16.57 | 0 | 0 | 0 | 5000 | 0 | 2.16 | -5000 | -10800 | 16.57 | -5000 | -82850
3.4 | Providing and laying Plum concrete ( Boulder mixed concrete) as per Drawing and Specifications, 60% M 15 concrete and 40% boulders/stones,Including Formwork using Mechanical Aids[2421] | Cum | 22.62 | 0 | 0 | 70.8 | 0 | 0 | 0 | 3500 | 0 | 22.62 | -3500 | -79170 | 70.8 | -3500 | -247800
4.1 | Compacting Original Ground, Compacting original ground supporting sub-grade, Loosening of the ground upto a level of 500 mm below the sub-grade level, watered, graded and compacted in layers as per Drawing and Technical Specifications. (Spec. cl. No: 1003, 1005) | Sqm | 423.26 | 0 | 0 | 2.33 | 0 | 0 | 0 | 0 | 0 | 423.26 | 0 | 0 | 2.33 | 0 | 0
4.2 | Providing and laying granular sub-base on prepared surface, mixing at OMC, and compacting to achieve the desired density, complete as per Drawing and Technical Specifications., By Mechanical means[1201] | Cum | 164.44 | 0 | 0 | 107.31 | 0 | 0 | #REF! | 0 | #REF! | #REF! | 0 | #REF! | #REF! | 0 | #REF!
4.3 | Providing and laying Crusher Run Macadam Base on a prepared surface, spreading and mixing , watering and compacting to form a layer of Base course as per Drawing and Technical Specifications., By Mix in Place Method [1204] | Cum | 57 | 0 | 0 | 161.21 | 0 | 0 | 0 | 0 | 0 | 57 | 0 | 0 | 161.21 | 0 | 0
| Total with PS amount |  |  |  | 0 |  |  | 0 |  |  | #REF! |  |  | #REF! |  |  | #REF!
| PS amount |  |  |  | 0 |  |  | 0 |  |  | 0 |  |  | -200000 |  |  | -200000
| Total without PS |  |  |  | 0 |  |  | 0 |  |  | #REF! |  |  | #REF! |  |  | #REF!
| VAT 13% |  |  |  | 0 |  |  | 0 |  |  | #REF! |  |  | #REF! |  |  | #REF!
| Grand Total Inclusive VAT and PS |  |  |  | 0 |  |  | 0 |  |  | #REF! |  |  | #REF! |  |  | #REF!
| क) स्वीकृत लागत अनुमान (इष्टिमेट) भन्दा घटि बढी खर्च रू...........प्रतिशत (%)...... |  |  |  |  | उपर्युक्तबमोजिम भएको कार्य सुरु सम्झौताको स्वीकृत डिजाइन र स्पेसिफिकेसनबमोजिम भएको छ/छैन।भेरिएशन आदेश र सर्तहरूबमोजमि भए/नभएकोहुँदा उक्त कार्य सम्पन्न भएको स्वीकार/ अस्वीकार गरिएको छ।
घटी/बढीको पुस्ट्याइँ..................................................................
स्वीकृत लागत अनुमान, डिजाइन र स्पेसिफिकेसनअनुसार काम भएको छ भनी सिफारिस गर्ने
| तयार गर्नेः |  |  | जाँच गर्नेः | [11 empty] | स्विकृत गर्ने:
| सहीः |  |  | सहीः | [11 empty] | सही:
| नामः रबिन लामिछाने/सुधांशु सुवेदी |  |  | नामः सागर भण्डारी | [11 empty] | कार्यालय प्रमुखको नाम: नवराज बास्तोला
| दर्जाःसब-ईन्जिनियर |  |  | दर्जाः ईन्जिनियर | [11 empty] | दर्जा: डिभिजन प्रमुख
| मितिः २०८१/०१/१४ |  |  | मितिः २०८१/०१/१४ | [11 empty] | मितिः २०८१/०१/१४
म.ले.प.फारम नं: ५१०
साबिकको फारम नं: १७६

## Abstract
a
b
c
d
e
f
Abstract of Cost
Contract Identification No:- xx
Name of Project:xx
Name of Works: xx
S.N. | Description of Works | Unit | Quantity | Rate (NRs) | Amount (NRs) | Remarks
1 | General works
1.1 | Relocation of services / minor infrastructures, Engineer's facility, Office accessories and equipments, Quality Control as per specifications and instruction of the Engineer.[111] | PS | 1 |  | 0
1.2 | Provision of Insurance for the loss or damage to the Works, Plant, and Materials; as per SCC 19.1 [SS 100] | Job | 1 |  | 0
| Sub-Total 1 |  |  |  | 0
2 | Earthwork
2.1 | Road way Excavation in all types (including hard rock) of soil as per Drawing and technical specifications including removal of stumps and other deleterious matter, all lifts and lead as per Drawing and instruction of the Engineer[905] | Cum | 3000 |  | 0
2.2 | Providing and laying of Plain/Reinforced Cement Concrete in Foundation complete as per Drawing and Technical Specifications, PCC Grade M 15 including formworks all complete.[2000] | Cum | 50 |  | 0
| Sub-Total 2 |  |  |  | 0
3 | Structural Works
3.1 | Excavation for Structures Foundation, Earth work in excavation of foundation of structures, including construction of shoring and bracing, removal of stumps and other deleterious matter & Backfilling with Suitable Material as per Drawing and Technical Specifications.,[907] | Cum | 443.18 |  | 0
3.2 | Providing and laying of hand pack Stone soling with 150 to 200 mm thick stones and packing with smaller stone on prepared surface as per Drawing and Technical Specifications.[1006] | Cum | 158.95 |  | 0
3.3 | Providing and laying of Plain Cement Concrete M 10 ( or 1:3:6 for nominal mix) in Foundation complete as per Drawing and Technical Specifications.[2000] | Cum | 2.16 |  | 0
3.4 | Providing and laying of Plain/Reinforced Cement Concrete in Foundation complete as per Drawing and Technical Specifications, PCC Grade M 15 including formworks all complete.[2000] | Cum | 22.62 |  | 0
3.5 | Providing and laying Plum concrete ( Boulder mixed concrete) as per Drawing and Specifications, 60% M 15 concrete and 40% boulders/stones,Including Formwork using Mechanical Aids[2421] | Cum | 423.26 |  | 0
3.6 | Random Rubble Masonry, Providing and laying of Stone Masonry Work in Cement Mortar 1:4 in Foundation complete as per Drawing and Technical Specifications., Using Concrete Mixer[2602,2603] | Cum | 164.44 |  | 0
3.7 | Providing, Assembling & providing and filling stone in mechanically woven double twisted crates / mattress including rolling, cutting and with lacing wire and binding wire as per specification , Hexagonal mesh type 100 mm x 120 mm, mesh wire 3 mm, selvage wire 3.9 mm, lacing wire 2.4 mm [SS 2402] | Cum | 97.5 |  | 0
3.8 | Laying and fixing of Geo-Textile all complete as per specification., Providing and laying of a geotextile filter between pitching and embankment slopes as per Drawing and Technical Specifications.[2404] | Sqm | 57 |  | 0
| Sub-Total 3 |  |  |  | 0
4 | Pavement Works
4.1 | Providing and laying of Plain/Reinforced Cement Concrete in Foundation complete as per Drawing and Technical Specifications., RCC Grade M 25/20 including formwork [2000] | Cum | 92.12 |  | 0
4.2 | Providing and laying , fitting and placing un-coated Mild steel / HYSD reinforcement complete in foundation as per drawing and technical specification [2014] | Ton | 3.83 |  | 0
| Sub-Total 4 |  | 0 |  | 0
Total (Excluding VAT, Contingencies and PS) |  |  |  |  | 0
Provisional Sum |  |  |  |  | 0
VAT (13%) |  |  |  |  | 0
Contingency (4%) |  |  |  |  | 0
Grand Total |  |  |  |  | 0

## Data (2)
Date of Measurement: 2081/10/19
Measurnment Number :- 01 |  |  | 1
Bill No.:1st Running Bill |  | F/Y:- 81/82 | 1
Name of Project: Road Improvement Works on Bhyakute Pandhera Shikhardanda-Thamdanda Dhnaubase Road, Galyang Municipality 11, Syangja |  |  | Road Improvement Works on Bhyakute Pandhera Shikhardanda-Thamdanda Dhnaubase Road, Galyang Municipality 11, Syangja
Name of Works: Road Improvement Works |  |  | Road Improvement Works
Project Implement place :- Bhyakute Pandhera Shikhardanda-Thamdanda Dhnaubase Road, Galyang Municipality 11, Syangja |  |  | Bhyakute Pandhera Shikhardanda-Thamdanda Dhnaubase Road, Galyang Municipality 11, Syangja
Contract Identification No:- RDPKR/337011694/81/82-23 |  |  | RDPKR/337011694/81/82-23
Client : - Road Division , Pokhara |  |  | Road Division , Pokhara
Name of Contractor: M/S Gejha Kalika Construction Pvt.Ltd,Galyang-3 Syangja |  |  | M/S Gejha Kalika Construction Pvt.Ltd,Galyang-3 Syangja
Agreement Date: 2081/07/26 |  |  | 2081/07/26
Date of Completion: 2082/02/20 |  |  | 2082/02/20
Time Extension : -
Date of Work Order: 2081/07/26 |  |  | 2081/07/26
New Completion Date after Variation:
Work completed Date :- Running
Date of Work Order: 2081/07/26 |  |  | 2081/07/26
Client :- Road Division , Pokhara
Division Chief/ Project Manager :- |  |  | Nawaraj Bastola
Pan no :-
Submitted by :
Address:
Name Of Road: Bhyakute Pandhera Shikhardanda-Thamdanda Dhnaubase Road, Galyang Municipality 11, Syangja
Government of Nepal
Ministry of Physical Infrastructure and Transport
Department of Roads
Federal Road Supervision and Monitoring Office Pokhara
Road Division Pokhara
Kaski

## reason
a
Ministry of Physical Infrastructure & Transport
Department of Roads
Federal Road Supervision and Monitoring Office
Road Division Pokhara
Kaski
Name of Project:xx
Contract Identification No:- xx
Name of Contractor: xx
Date of Work Order: xx
Date of Completion:xx
Revised Estimate/Variation No. 1
Reason for Variation
Item No. | Description | Unit | Initial Quantity | Revised Quantity | Original Cost Estimate in NRs | Revised Cost Estimate in NRs | Original Contract Amount in NRs | Revised Contract Amount in NRs | % Change in Quantity | Change in Contract Amount | % Increment wrt Initial Contract Amount | Rate Negotiation Required or Not | Reason
1 | General works
1.1 | Relocation of services / minor infrastructures, Engineer's facility, Office accessories and equipments, Quality Control as per specifications and instruction of the Engineer.[111] | PS | 1 | 0 | 0 | 0 | 50000 | 0
1.2 | Provision of Insurance for the loss or damage to the Works, Plant, and Materials; as per SCC 19.1 [SS 100] | Job | 1 | 0 | 0 | 0 | 50000 | 0
2 | Structures Works/Pavement Works
2.1 | Road way Excavation in all types (including hard rock) of soil as per Drawing and technical specifications including removal of stumps and other deleterious matter, all lifts and lead as per Drawing and instruction of the Engineer[905] | Cum | 3000 | 0 | 0 | 0 | 240000 | 0
2.2 | Providing and laying of Plain/Reinforced Cement Concrete in Foundation complete as per Drawing and Technical Specifications, PCC Grade M 15 including formworks all complete.[2000] | Cum | 50 | 0 | 0 | 0 | 240000 | 0
3 | Structural Works
3.1 | Excavation for Structures Foundation, Earth work in excavation of foundation of structures, including construction of shoring and bracing, removal of stumps and other deleterious matter & Backfilling with Suitable Material as per Drawing and Technical Specifications.,[907] | Cum | 443.18 | 0 | 0 | 0 | 22159 | 0
3.2 | Providing and laying of hand pack Stone soling with 150 to 200 mm thick stones and packing with smaller stone on prepared surface as per Drawing and Technical Specifications.[1006] | Cum | 158.95 | 0 | 0 | 0 | 349690 | 0
3.3 | Providing and laying of Plain Cement Concrete M 10 ( or 1:3:6 for nominal mix) in Foundation complete as per Drawing and Technical Specifications.[2000] | Cum | 2.16 | 0 | 0 | 0 | 12960 | 0
3.4 | Providing and laying of Plain/Reinforced Cement Concrete in Foundation complete as per Drawing and Technical Specifications, PCC Grade M 15 including formworks all complete.[2000] | Cum | 22.62 | 0 | 0 | 0 | 158340 | 0
3.5 | Providing and laying Plum concrete ( Boulder mixed concrete) as per Drawing and Specifications, 60% M 15 concrete and 40% boulders/stones,Including Formwork using Mechanical Aids[2421] | Cum | 423.26 | 0 | 0 | 0 | 2645375 | 0
3.6 | Random Rubble Masonry, Providing and laying of Stone Masonry Work in Cement Mortar 1:4 in Foundation complete as per Drawing and Technical Specifications., Using Concrete Mixer[2602,2603] | Cum | 164.44 | 0 | 0 | 0 | 822200 | 0
3.7 | Providing, Assembling & providing and filling stone in mechanically woven double twisted crates / mattress including rolling, cutting and with lacing wire and binding wire as per specification , Hexagonal mesh type 100 mm x 120 mm, mesh wire 3 mm, selvage wire 3.9 mm, lacing wire 2.4 mm [SS 2402] | Cum | 97.5 | 0 | 0 | 0 | 341250 | 0
3.8 | Laying and fixing of Geo-Textile all complete as per specification., Providing and laying of a geotextile filter between pitching and embankment slopes as per Drawing and Technical Specifications.[2404] | Sqm | 57 | 0 | 0 | 0 | 3990 | 0
4 | Pavement Works
4.1 | Providing and laying of Plain/Reinforced Cement Concrete in Foundation complete as per Drawing and Technical Specifications., RCC Grade M 25/20 including formwork [2000] | Cum | 92.12 | 0 | 0 | 0 | 736960 | 0
4.2 | Providing and laying , fitting and placing un-coated Mild steel / HYSD reinforcement complete in foundation as per drawing and technical specification [2014] | Ton | 3.83 | 0 | 0 | 0 | 421300 | 0

## VOnego
a
b
c
d
e
f
Negotiation Rate for New/ Additional Item
S.N. | BOQ Item No | Description | Unit | Departmental Rate (Excl. VAT) | Submitted Rate (Excl. VAT) | Decreased % wrt Departmental Rate | Negotiated Rate (Excl. VAT) | Decreased % wrt Departmental Rate
1 | [5 empty] | #DIV/0! |  | #DIV/0!
Binding Signature of Contractor
Binding Signature of Employer
Division Chief
Witness
Account Officer

## cover page VO
a | Government of Nepal | Government of Nepal
b | Government of Nepal | Government of Nepal
c | Government of Nepal | Government of Nepal
d | Government of Nepal | Government of Nepal
e | Government of Nepal | Government of Nepal
f | Government of Nepal | Government of Nepal
Name of Project:xx
Contract Identification No:- xx
Variation Order VO-1
Submitted By: |  | Submitted to:
Name of Contractor: xx |  | xx

## summary of variation
a
b
c
d
e
f
I. | Information
1 | Contract No. |  |  | :- | - xx
2 | Employer |  |  | :- | xx
3 | Division Chief/ Project Manager |  |  | :- | :-
4 | Contractor |  |  | :- | xx
5 | Date of application submitted in office |  |  | :-
6 | Reason for variation |  |  | :-
II. | About Cost & Time
1 | Original Cost Estimate ( Without Vat and PS ) |  |  | :- | 0
3 | Cost Estimate after this variation ( Without Vat and PS ) |  |  | :- | 0
4 | Original Agreement Amount ( Without Vat and PS ) |  |  | :- | 5465094
6 | Agreement Amount after this Variation ( Without Vat and PS ) |  |  | :- | 0
7 | % increase or decrease in cost Estimate |  |  | :- | #DIV/0!
8 | % increase or decrease in Agreement Amount |  |  | :- | -100%
9 | Time extension required or not |  |  | :- | Not
10 | Required time duration if time extended |  |  | :- | Not
11 | Settlement of Rate for New item required or not |  |  | :- | Not
12 | About arrangement of additional financial liabilities |  |  | :- | Not
due to variation
Prepared by |  | Checked by | Certified & Recommended by |  |  | Approved by

## VO
a | Government of Nepal | Government of Nepal | Government of Nepal | Government of Nepal | Government of Nepal | Government of Nepal | Government of Nepal | Government of Nepal | Government of Nepal | Government of Nepal | Government of Nepal | Government of Nepal | Government of Nepal | Government of Nepal | Government of Nepal | Government of Nepal | Government of Nepal | Government of Nepal | Government of Nepal | Government of Nepal | Government of Nepal | Government of Nepal | Government of Nepal
b | Government of Nepal | Government of Nepal | Government of Nepal | Government of Nepal | Government of Nepal | Government of Nepal | Government of Nepal | Government of Nepal | Government of Nepal | Government of Nepal | Government of Nepal | Government of Nepal | Government of Nepal | Government of Nepal | Government of Nepal | Government of Nepal | Government of Nepal | Government of Nepal | Government of Nepal | Government of Nepal | Government of Nepal | Government of Nepal | Government of Nepal
c | Government of Nepal | Government of Nepal | Government of Nepal | Government of Nepal | Government of Nepal | Government of Nepal | Government of Nepal | Government of Nepal | Government of Nepal | Government of Nepal | Government of Nepal | Government of Nepal | Government of Nepal | Government of Nepal | Government of Nepal | Government of Nepal | Government of Nepal | Government of Nepal | Government of Nepal | Government of Nepal | Government of Nepal | Government of Nepal | Government of Nepal
d | Government of Nepal | Government of Nepal | Government of Nepal | Government of Nepal | Government of Nepal | Government of Nepal | Government of Nepal | Government of Nepal | Government of Nepal | Government of Nepal | Government of Nepal | Government of Nepal | Government of Nepal | Government of Nepal | Government of Nepal | Government of Nepal | Government of Nepal | Government of Nepal | Government of Nepal | Government of Nepal | Government of Nepal | Government of Nepal | Government of Nepal
e | Government of Nepal | Government of Nepal | Government of Nepal | Government of Nepal | Government of Nepal | Government of Nepal | Government of Nepal | Government of Nepal | Government of Nepal | Government of Nepal | Government of Nepal | Government of Nepal | Government of Nepal | Government of Nepal | Government of Nepal | Government of Nepal | Government of Nepal | Government of Nepal | Government of Nepal | Government of Nepal | Government of Nepal | Government of Nepal | Government of Nepal
f | Government of Nepal | Government of Nepal | Government of Nepal | Government of Nepal | Government of Nepal | Government of Nepal | Government of Nepal | Government of Nepal | Government of Nepal | Government of Nepal | Government of Nepal | Government of Nepal | Government of Nepal | Government of Nepal | Government of Nepal | Government of Nepal | Government of Nepal | Government of Nepal | Government of Nepal | Government of Nepal | Government of Nepal | Government of Nepal | Government of Nepal
Variation Order - 01
Name of Project:xx
Project Implement place :- xx | [16 empty] | Agreement Date: 2081/07/26
Financed By: Government of Nepal | [16 empty] | New Completion Date after Variation:
Contract Identification No:- xx | [16 empty] | Increase or decrease with original Cost Estimate: |  |  |  |  | 0
Client :- xx | [16 empty] | Percentage increase or decrease with Original Cost Estimate: |  |  |  |  | #DIV/0!
Name of Contractor: xx | [16 empty] | Cost Estimate after Variation Order (excluding VAT& PS): |  |  |  |  | 0
Original Cost Estimate(excluding VAT & PS) |  |  | 0 | [13 empty] | Percentage increase or decrease with original Contract Amount: |  |  |  |  | -100%
Original Contract Amount(excluding VAT & PS) |  |  | 5465094 | [13 empty] | Budgetery provision for increased works
Revised Contract Amount(excluding VAT & PS) |  |  | 0
Actual Expenditure till date( excluding vat and PS)
S.N | Item No. | Description of Item | Unit | Original Cost Amount |  |  | Revised Cost Estimates (VO 1) |  |  | % change in Quantity w.r.t original | % Change in Amount with respect to original cost estimates | *परिमार्जित लागत रकम.. (VO 2) |  |  | सुरु लागतको आधारमा भएको थप घटको % | Original Contract Amount (NRs) |  | *कायम सम्झौता रकम...२ |  | Revised Contract Amount After VO 1 |  | % change in Amount with respect to original Contact Amount | Reason for Changes in Quantity/ Rate
|  |  |  | Quantity | Rate (NRS) | Amount (NRS) | Quantity | Rate (NRS) | Amount (NRS) |  |  | परिमाण | दर | जम्मा |  | Rate (NRS) | Amount (NRS) | दर | जम्मा रकम | Rate (NRS) | Amount (NRS)
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 |  | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 20 | 21 | 18 | 19 | 22 | 23
1 | 1 | General works
2 | 1.1 | Relocation of services / minor infrastructures, Engineer's facility, Office accessories and equipments, Quality Control as per specifications and instruction of the Engineer.[111] | PS | 1 | 0 | 0 | 0 | 0 | 0 | -100 | 11: #DIV/0!; 16: 50000; 17: 50000; 18: 50000; 19: 0; 22: -0.9148% | -200000
3 | 1.2 | Provision of Insurance for the loss or damage to the Works, Plant, and Materials; as per SCC 19.1 [SS 100] | Job | 1 | 0 | 0 | 0 | 0 | 0 | -100 | 11: #DIV/0!; 16: 50000; 17: 50000; 18: 50000; 19: 0; 22: -0.9148% | -250000
4 |  | Sub-Total 1 |  |  | 0 | 0 |  |  | 0 |  | 16: 0; 17: 100000; 19: 0
5 | 2 | Earthwork
6 | 2.1 | Road way Excavation in all types (including hard rock) of soil as per Drawing and technical specifications including removal of stumps and other deleterious matter, all lifts and lead as per Drawing and instruction of the Engineer[905] | Cum | 3000 | 0 | 0 | 0 | 0 | 0 | -100 | 11: #DIV/0!; 16: 80; 17: 240000; 18: 80; 19: 0; 22: -4.392% | 0
7 | 2.2 | Providing and laying of Plain/Reinforced Cement Concrete in Foundation complete as per Drawing and Technical Specifications, PCC Grade M 15 including formworks all complete.[2000] | Cum | 50 | 0 | 0 | 0 | 0 | 0 | -100 | 11: #DIV/0!; 16: 8000; 17: 240000; 18: 8000; 19: 0; 22: -4.392%
8 |  | Sub-Total 2 |  |  | 0 | 0 |  |  | 0 |  | 17: 480000; 19: 0
9 | 3 | Structural Works
10 | 3.1 | Excavation for Structures Foundation, Earth work in excavation of foundation of structures, including construction of shoring and bracing, removal of stumps and other deleterious matter & Backfilling with Suitable Material as per Drawing and Technical Specifications.,[907] | Cum | 443.18 | 0 | 0 | 0 | 0 | 0 | -100 | 11: #DIV/0!; 16: 50; 17: 22159; 18: 50; 19: 0; 22: -0.4054%
11 | 3.2 | Providing and laying of hand pack Stone soling with 150 to 200 mm thick stones and packing with smaller stone on prepared surface as per Drawing and Technical Specifications.[1006] | Cum | 158.95 | 0 | 0 | 0 | 0 | 0 | -100 | 11: #DIV/0!; 16: 2200; 17: 349690; 18: 2200; 19: 0; 22: -6.399%
12 | 3.3 | Providing and laying of Plain Cement Concrete M 10 ( or 1:3:6 for nominal mix) in Foundation complete as per Drawing and Technical Specifications.[2000] | Cum | 2.16 | 0 | 0 | 0 | 0 | 0 | -100 | 11: #DIV/0!; 16: 6000; 17: 12960; 18: 6000; 19: 0; 22: -0.2371%
13 | 3.4 | Providing and laying of Plain/Reinforced Cement Concrete in Foundation complete as per Drawing and Technical Specifications, PCC Grade M 15 including formworks all complete.[2000] | Cum | 22.62 | 0 | 0 | 0 | 0 | 0 | -100 | 11: #DIV/0!; 16: 7000; 17: 158340; 18: 7000; 19: 0; 22: -2.897%
14 | 3.5 | Providing and laying Plum concrete ( Boulder mixed concrete) as per Drawing and Specifications, 60% M 15 concrete and 40% boulders/stones,Including Formwork using Mechanical Aids[2421] | Cum | 423.26 | 0 | 0 | 0 | 0 | 0 | -100 | 11: #DIV/0!; 16: 6250; 17: 2645375; 18: 6250; 19: 0; 22: -48.4%
15 | 3.6 | Random Rubble Masonry, Providing and laying of Stone Masonry Work in Cement Mortar 1:4 in Foundation complete as per Drawing and Technical Specifications., Using Concrete Mixer[2602,2603] | Cum | 164.44 | 0 | 0 | 0 | 0 | 0 | -100 | 11: #DIV/0!; 16: 5000; 17: 822200; 18: 5000; 19: 0; 22: -15.04%
16 | 3.7 | Providing, Assembling & providing and filling stone in mechanically woven double twisted crates / mattress including rolling, cutting and with lacing wire and binding wire as per specification , Hexagonal mesh type 100 mm x 120 mm, mesh wire 3 mm, selvage wire 3.9 mm, lacing wire 2.4 mm [SS 2402] | Cum | 97.5 | 0 | 0 | 0 |  | 0 | -100 | 11: #DIV/0!; 16: 3500; 17: 341250; 18: 3500; 19: 0; 22: -6.244%
17 | 3.8 | Laying and fixing of Geo-Textile all complete as per specification., Providing and laying of a geotextile filter between pitching and embankment slopes as per Drawing and Technical Specifications.[2404] | Sqm | 57 | 0 |  | 0 |  |  | -100 | 11: #DIV/0!; 16: 70; 17: 3990; 18: 70; 19: 0; 22: -0.073%
18 | 0 | Sub-Total 3 |  |  |  | 0 |  |  | 0 | #DIV/0! | 17: 4355964; 19: 0
19 | 4 | Pavement Works
20 | 4.1 | Providing and laying of Plain/Reinforced Cement Concrete in Foundation complete as per Drawing and Technical Specifications., RCC Grade M 25/20 including formwork [2000] | Cum | 92.12 | 0 | 0 | 0 | 0 | 0 | -100 | 11: #DIV/0!; 16: 8000; 17: 736960; 18: 8000; 19: 0; 22: -13.48%
21 | 4.2 | Providing and laying , fitting and placing un-coated Mild steel / HYSD reinforcement complete in foundation as per drawing and technical specification [2014] | Ton | 3.83 | 0 | 0 | 0 | 0 | 0 | -100 | 11: #DIV/0!; 16: 110000; 17: 421300; 18: 110000; 19: 0; 22: -7.709%
22 |  | Sub-Total 4 |  |  |  | 0 |  | 0 | 0 | #DIV/0! | 11: #DIV/0!; 17: 0; 19: 0; 22: 0%
|  | Total Including PS |  |  |  | 0 |  |  | 0 |  | 17: 5515094; 19: 0
|  | Total EXcluding PS |  |  |  | 0 |  |  | 0 |  | 17: 5465094; 19: 0
|  | Vat@13% |  |  |  | 0 |  |  | 0 |  | 17: 710462.22; 19: 0
|  | Total with VAT and PS |  |  |  | 0 |  |  | 0 |  | 17: 6225556.22; 19: 0
म.ले.प.फारम नं: ५०८

## Variation Checklist
a
b
c
d
e
f
e]l/P;g cfb]z ;DalGw ljj/0f
l;=g+= | ljifo | ljj/0f
! | of]hgf⁄sfof{nosf] gfd | Road Division , Pokhara
@ | 7]Ssf g+= / gfd | - xx & xx
# | l8hfOg sG;N6]G6 k¦fljlwssf] gfd | gePsf]
$ | ;'k/lehg sG;N6]G6 k¦fljlwssf] gfd | gePsf]
% | 7]Ssf sfo{sf] k¦s[lt / d'Vo sfo{ | xx
^ | z'? Nffut cg'dfg c+s-Eof6 slG6Gh]lG;h jfx]s_ ?= | 0
& | e]l/P;g kZrft sfod x'g] Nffut cg'dfg c+s-Eof6 slG6Gh]lG;h jfx]s_?= | 0
* | nfut cg'dfg 36L jf j9L k¦ltzt | #DIV/0!
( | z'? ;Demf}tf c+s-Eof6 slG6Gh]lG;h jfx]s_ ?= | 5465094
!) | e]l/P;g kZrft sfod /sd -Eof6 slG6Gh]lG;h jfx]s_ | 0
!! | 7]Ssf c+sdf 36L jf j9L k¦ltzt | -100%
!@ | e]l/P;g ug'{kgf{sf] sf/0f -d'Vo yk36 ePsf] ljj/0f_ | ;+nUg 5
!# | e]l/P;gn] 7]Ssf cjlw a9\g] jf ga9\g] | ga9\g]
!$ | e]l/P;gdf gof+ cfO6d ePsf] gePsf] | gePsf]
!% | e]l/P;gdf gof+ b//]6 ePsf] gePsf] | gePsf]
!^ | lgdf{0fsfo{sf] Drawing ,Design tyf Specification jbNg' kg]{ jf gkg]{
!& | jbNg'kg]{ ePdf lgdf{0f sfo{sf] cfwf/e"t k¦s[lt jf If]q kl/jt{g x'g] jf gx'g] | gx'g]
!* | e]l/P;gsf] sf/0f x'g] nfut cg'dfgsf] ;+;f]wg z'? Nfut cg'dfgsf] @% k¦ltzt eGbf a9L km/s k/] gk/]sf] | gePsf]
!( | z'?df c:jefljs nfut cg'dfg tof/ u/]sf] sf/0fn] v/Lb sfo{ k¦efljt x'g] jf gx'g] | gx'g]
@) | :jLs[t ah]6 tyf sfo{qmddf k/] jf gk/]sf] | k/]sf]
@! | e]l/P;gsf] k¦fljlws k'i6\ofO{+ eP jf gePsf] | ePsf]
@@ | e]l/P;g kmd{]6 eP jf gePsf] | ePsf]

## Revised Abstract
a
b
c
d
e
f
Abstract of Cost
Contract Identification No:- xx
Name of Project:xx
Name of Works: xx
S.N. | Description of works | Unit | Quantity | Rate (NRs) | Amount (NRs) | Remarks
1 | General works
1.1 | Relocation of services / minor infrastructures, Engineer's facility, Office accessories and equipments, Quality Control as per specifications and instruction of the Engineer.[111] | PS | 0 | 0 | 0 |  | &
1.2 | Provision of Insurance for the loss or damage to the Works, Plant, and Materials; as per SCC 19.1 [SS 100] | Job | 0 | 0 | 0
2 | Earthwork
2.1 | Road way Excavation in all types (including hard rock) of soil as per Drawing and technical specifications including removal of stumps and other deleterious matter, all lifts and lead as per Drawing and instruction of the Engineer[905] | Cum | 0 | 0 | 0
2.2 | Providing and laying of Plain/Reinforced Cement Concrete in Foundation complete as per Drawing and Technical Specifications, PCC Grade M 15 including formworks all complete.[2000] | Cum | 0 | 0 | 0
3 | Structural Works
3.1 | Excavation for Structures Foundation, Earth work in excavation of foundation of structures, including construction of shoring and bracing, removal of stumps and other deleterious matter & Backfilling with Suitable Material as per Drawing and Technical Specifications.,[907] | Cum | 0 | 0 | 0
3.2 | Providing and laying of hand pack Stone soling with 150 to 200 mm thick stones and packing with smaller stone on prepared surface as per Drawing and Technical Specifications.[1006] | Cum | 0 | 0 | 0
3.3 | Providing and laying of Plain Cement Concrete M 10 ( or 1:3:6 for nominal mix) in Foundation complete as per Drawing and Technical Specifications.[2000] | Cum | 0 | 0 | 0
3.4 | Providing and laying of Plain/Reinforced Cement Concrete in Foundation complete as per Drawing and Technical Specifications, PCC Grade M 15 including formworks all complete.[2000] | Cum | 0 | 0 | 0
3.5 | Providing and laying Plum concrete ( Boulder mixed concrete) as per Drawing and Specifications, 60% M 15 concrete and 40% boulders/stones,Including Formwork using Mechanical Aids[2421] | Cum | 0 | 0 | 0
3.6 | Random Rubble Masonry, Providing and laying of Stone Masonry Work in Cement Mortar 1:4 in Foundation complete as per Drawing and Technical Specifications., Using Concrete Mixer[2602,2603] | Cum | 0 | 0 | 0
3.7 | Providing, Assembling & providing and filling stone in mechanically woven double twisted crates / mattress including rolling, cutting and with lacing wire and binding wire as per specification , Hexagonal mesh type 100 mm x 120 mm, mesh wire 3 mm, selvage wire 3.9 mm, lacing wire 2.4 mm [SS 2402] | Cum |  | 0
3.8 | Laying and fixing of Geo-Textile all complete as per specification., Providing and laying of a geotextile filter between pitching and embankment slopes as per Drawing and Technical Specifications.[2404] | Sqm |  | 0
| Sub-Total 3 |  |  | 0 | 0
4 | Pavement Works |  |  | 0 | 0
4.1 | Providing and laying of Plain/Reinforced Cement Concrete in Foundation complete as per Drawing and Technical Specifications., RCC Grade M 25/20 including formwork [2000] | Cum |  | 0 | 0
4.2 | Providing and laying , fitting and placing un-coated Mild steel / HYSD reinforcement complete in foundation as per drawing and technical specification [2014] | Ton |  | 0 | 0
Sub-Total 4
Total (Excluding VAT, Contingencies and PS) |  |  |  |  | 0
Provisional Sum |  |  |  |  | 0
VAT (13%) |  |  |  |  | 0
Contingency (4%) |  |  |  |  | 0
Grand Total |  |  |  |  | 0

## Revised Quantity Sheet
a | Government of Nepal | Government of Nepal | Government of Nepal | Government of Nepal | Government of Nepal | Government of Nepal | Government of Nepal | Government of Nepal
b | Government of Nepal | Government of Nepal | Government of Nepal | Government of Nepal | Government of Nepal | Government of Nepal | Government of Nepal | Government of Nepal
c | Government of Nepal | Government of Nepal | Government of Nepal | Government of Nepal | Government of Nepal | Government of Nepal | Government of Nepal | Government of Nepal
d | Government of Nepal | Government of Nepal | Government of Nepal | Government of Nepal | Government of Nepal | Government of Nepal | Government of Nepal | Government of Nepal
e | Government of Nepal | Government of Nepal | Government of Nepal | Government of Nepal | Government of Nepal | Government of Nepal | Government of Nepal | Government of Nepal
f | Government of Nepal | Government of Nepal | Government of Nepal | Government of Nepal | Government of Nepal | Government of Nepal | Government of Nepal | Government of Nepal
Revised Abstract of Cost
F/Y:- 81/82
Contract Identification No:- xx
Name of Project:xx
Name of Works: xx
S.N. | Description of Works | Unit | No. | Length (m) | Breadth (m) | Height (m) | Quantity | Remarks
1 | General works
1.1 | Relocation of services / minor infrastructures, Engineer's facility, Office accessories and equipments, Quality Control as per specifications and instruction of the Engineer.[111] | PS |  |  |  |  | 0
1.2 | Provision of Insurance for the loss or damage to the Works, Plant, and Materials; as per SCC 19.1 [SS 100] | Job |  |  |  |  | 0
2 | Earthwork
2.1 | Road way Excavation in all types (including hard rock) of soil as per Drawing and technical specifications including removal of stumps and other deleterious matter, all lifts and lead as per Drawing and instruction of the Engineer[905] | Cum |  |  |  |  | 0
2.2 | Providing and laying of Plain/Reinforced Cement Concrete in Foundation complete as per Drawing and Technical Specifications, PCC Grade M 15 including formworks all complete.[2000] | Rm. |  |  |  |  | 0
3 | Structural Works
3.1 | Excavation for Structures Foundation, Earth work in excavation of foundation of structures, including construction of shoring and bracing, removal of stumps and other deleterious matter & Backfilling with Suitable Material as per Drawing and Technical Specifications.,[907] | Cum |  |  |  |  | 0
3.2 | Providing and laying of hand pack Stone soling with 150 to 200 mm thick stones and packing with smaller stone on prepared surface as per Drawing and Technical Specifications.[1006] | Cum |  |  |  |  | 0
3.3 | Providing and laying of Plain Cement Concrete M 10 ( or 1:3:6 for nominal mix) in Foundation complete as per Drawing and Technical Specifications.[2000] | Cum |  |  |  |  | 0
3.4 | Providing and laying of Plain/Reinforced Cement Concrete in Foundation complete as per Drawing and Technical Specifications, PCC Grade M 15 including formworks all complete.[2000] | Cum |  |  |  |  | 0
3.5 | Providing and laying Plum concrete ( Boulder mixed concrete) as per Drawing and Specifications, 60% M 15 concrete and 40% boulders/stones,Including Formwork using Mechanical Aids[2421] | Cum |  |  |  |  | 0
3.6 | Random Rubble Masonry, Providing and laying of Stone Masonry Work in Cement Mortar 1:4 in Foundation complete as per Drawing and Technical Specifications., Using Concrete Mixer[2602,2603] | Sqm |  |  |  |  | 0
3.7 | Providing, Assembling & providing and filling stone in mechanically woven double twisted crates / mattress including rolling, cutting and with lacing wire and binding wire as per specification , Hexagonal mesh type 100 mm x 120 mm, mesh wire 3 mm, selvage wire 3.9 mm, lacing wire 2.4 mm [SS 2402] | [5 empty] | 0
3.8 | Laying and fixing of Geo-Textile all complete as per specification., Providing and laying of a geotextile filter between pitching and embankment slopes as per Drawing and Technical Specifications.[2404] | [5 empty] | 0
4 | Pavement Works
4.1 | Providing and laying of Plain/Reinforced Cement Concrete in Foundation complete as per Drawing and Technical Specifications., RCC Grade M 25/20 including formwork [2000] | Sqm |  |  |  |  | 0
4.2 | Providing and laying , fitting and placing un-coated Mild steel / HYSD reinforcement complete in foundation as per drawing and technical specification [2014] | Cum |  |  |  |  | 0

## cover page
a | Government of Nepal | Government of Nepal
b | Government of Nepal | Government of Nepal
c | Government of Nepal | Government of Nepal
d | Government of Nepal | Government of Nepal
e | Government of Nepal | Government of Nepal
f | Government of Nepal | Government of Nepal
Name of Project:xx
Contract Identification No:- xx
Bill No.:1st Running Bill
Submitted By: |  | Submitted to:
Name of Contractor: xx |  | xx

## Front Sheet
Government of Nepal | Government of Nepal | Government of Nepal | Government of Nepal | Government of Nepal
Ministry of Physical Infrastructure and Transport | Ministry of Physical Infrastructure and Transport | Ministry of Physical Infrastructure and Transport | Ministry of Physical Infrastructure and Transport | Ministry of Physical Infrastructure and Transport
Department of Roads | Department of Roads | Department of Roads | Department of Roads | Department of Roads
Federal Road Supervision and Monitoring Office Pokhara | Federal Road Supervision and Monitoring Office Pokhara | Federal Road Supervision and Monitoring Office Pokhara | Federal Road Supervision and Monitoring Office Pokhara | Federal Road Supervision and Monitoring Office Pokhara
Road Division Pokhara | Road Division Pokhara | Road Division Pokhara | Road Division Pokhara | Road Division Pokhara
Kaski | Kaski | Kaski | Kaski | Kaski
Payment Summary Sheet
Bill No.:1st Running Bill |  | Original Contract Amount including (VAT) : |  | 6406356.22
Name of Project:xx |  | Original Contract Amount excluding(VAT) : |  | 5675094
I Installment Mobilization Advance:
II Installment Mobilization Advance:
Name of Works: xx |  | Total Mobilization Advance:
Date of Work Order: xx |  | Deduction of Mobilization Advance:
Work Completed Date:- Running |  | Mobilization Advance Outstanding: |  | 0
Date of Completion:xx |  | Contract Identification No.: |  | - xx
Period of Defect Liability: 365days
S.N. | Description | Current IPC | Previous IPC | Total to Date
A | Total Amount with PS | 0 | 0 | 0
B | PS Amount | 0 | 0 | 0
C | Total Amount without PS | 0 | 0 | 0
D | VAT @ 13% of C | 0 | 0 | 0
E | Total Bill Amount (A+D) | 0 | 0 | 0
F | Deduction
G | Retention money @ 5% of A | 0 | 0 | 0
H | Advance Payment Deduction | 0 | 0 | 0
I | Advance Income Tax @1.5% A | 0 | 0 | 0
J | Liquidated Damages (if any) | 0 | 0 | 0
K | Contractor's Development Fund @ 0.1% of A | 0 | 0 | 0
L | 30 % VAT deposited in Revenue account of D | 0 | 0 | 0
M | Total Deduction | 0 | 0 | 0
N | Total Amount Payable to the Contractor Including VAT (F-M) | 0 | 0 | 0
O | Local Currency | 0 | 0 | 0
Name of Contractor: xx |  | Checked by:
Contractor |  | DOR Sub-Engineer
Date: |  | Date:
Checked by: |  | Checked by: |  | Approved by:
DoR Engineer |  | DoR Accountant | DoR Chief Accountant | Division Chief
Date: |  | Date: | Date: | Date:

## Data
Date of Measurement: 2081/11/11
Measurnment Number :- 01 |  | 1
Bill No.:1st Running Bill | F/Y:- 81/82 | 1
Name of Project:xx |  | xx
Name of Works: xx |  | xx
Project Implement place :- xx |  | - xx
Contract Identification No:- xx |  | - xx
Client : - xx |  | xx
Name of Contractor: xx |  | xx
Agreement Date: 2081/07/26 |  | 2081/07/26
Date of Completion:xx |  | xx
Time Extension : -
Date of Work Order: xx |  | xx
New Completion Date after Variation:
Work completed Date :- Running
Date of Work Order: xx |  | xx
Client :- xx |  | xx
Division Chief/ Project Manager :- |  | :-
Pan no :-
Submitted by :
Address:

## BOQ
a | Government of Nepal | Government of Nepal | Government of Nepal | Government of Nepal | Government of Nepal | Government of Nepal | Government of Nepal | Government of Nepal | Government of Nepal | Government of Nepal | Government of Nepal | Government of Nepal | Government of Nepal | Government of Nepal | Government of Nepal | Government of Nepal | Government of Nepal
b | Ministry of Physical Infrastructure and Transport | Ministry of Physical Infrastructure and Transport | Ministry of Physical Infrastructure and Transport | Ministry of Physical Infrastructure and Transport | Ministry of Physical Infrastructure and Transport | Ministry of Physical Infrastructure and Transport | Ministry of Physical Infrastructure and Transport | Ministry of Physical Infrastructure and Transport | Ministry of Physical Infrastructure and Transport | Ministry of Physical Infrastructure and Transport | Ministry of Physical Infrastructure and Transport | Ministry of Physical Infrastructure and Transport | Ministry of Physical Infrastructure and Transport | Ministry of Physical Infrastructure and Transport | Ministry of Physical Infrastructure and Transport | Ministry of Physical Infrastructure and Transport | Ministry of Physical Infrastructure and Transport
c | Department of Roads | Department of Roads | Department of Roads | Department of Roads | Department of Roads | Department of Roads | Department of Roads | Department of Roads | Department of Roads | Department of Roads | Department of Roads | Department of Roads | Department of Roads | Department of Roads | Department of Roads | Department of Roads | Department of Roads
d | Federal Road Supervision and Monitoring Office Pokhara | Federal Road Supervision and Monitoring Office Pokhara | Federal Road Supervision and Monitoring Office Pokhara | Federal Road Supervision and Monitoring Office Pokhara | Federal Road Supervision and Monitoring Office Pokhara | Federal Road Supervision and Monitoring Office Pokhara | Federal Road Supervision and Monitoring Office Pokhara | Federal Road Supervision and Monitoring Office Pokhara | Federal Road Supervision and Monitoring Office Pokhara | Federal Road Supervision and Monitoring Office Pokhara | Federal Road Supervision and Monitoring Office Pokhara | Federal Road Supervision and Monitoring Office Pokhara | Federal Road Supervision and Monitoring Office Pokhara | Federal Road Supervision and Monitoring Office Pokhara | Federal Road Supervision and Monitoring Office Pokhara | Federal Road Supervision and Monitoring Office Pokhara | Federal Road Supervision and Monitoring Office Pokhara
e | Road Division Pokhara | Road Division Pokhara | Road Division Pokhara | Road Division Pokhara | Road Division Pokhara | Road Division Pokhara | Road Division Pokhara | Road Division Pokhara | Road Division Pokhara | Road Division Pokhara | Road Division Pokhara | Road Division Pokhara | Road Division Pokhara | Road Division Pokhara | Road Division Pokhara | Road Division Pokhara | Road Division Pokhara
f | Kaski | Kaski | Kaski | Kaski | Kaski | Kaski | Kaski | Kaski | Kaski | Kaski | Kaski | Kaski | Kaski | Kaski | Kaski | Kaski | Kaski
Bill of Contract
Name of Works: xx | [11 empty] | Bill No.:1st Running Bill
Name of Project:xx | [11 empty] | Date of Work Order: xx
Name of Contractor: xx | [11 empty] | Date of Completion:xx
Contract Identification No:- xx | [11 empty] | Date of Time Extension:
Date of Measurement: 2081/11/11 | [8 empty] | Work Progress | 0% |  | Date of work completed:
S.N. | Work Description | Unit | As per BOQ |  |  | As per VO1 |  |  | Upto Date Work Till Date |  | Previous Bill |  | Current Bill |  | Remaining Bill |  | Remarks
|  |  | Quantity | Rate | Total Amount | Quantity | Rate | Total Amount | Quantity | Total Amount | Quantity | Total Amount | Quantity | Total Amount | Quantity | Total Amount
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18
1 | General works
1.1 | Relocation of services / minor infrastructures, Engineer's facility, Office accessories and equipments, Quality Control as per specifications and instruction of the Engineer.[111] | PS | 1 | 50000 | 50000 |  | 50000 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | #REF!
1.2 | Provision of Insurance for the loss or damage to the Works, Plant, and Materials; as per SCC 19.1 [SS 100] | Job | 1 | 50000 | 50000 |  | 50000 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | #REF!
| Sub-Total 1 |  |  |  | 100000 |  |  |  |  | 0 |  | 0 |  | 0
2 | Earthwork | [13 empty] | 0 |  |  | #REF!
2.1 | Road way Excavation in all types (including hard rock) of soil as per Drawing and technical specifications including removal of stumps and other deleterious matter, all lifts and lead as per Drawing and instruction of the Engineer[905] | Cum | 3000 | 80 | 240000 |  | 80 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 |  |  | #REF!
2.2 | Providing and laying of Plain/Reinforced Cement Concrete in Foundation complete as per Drawing and Technical Specifications, PCC Grade M 15 including formworks all complete.[2000] | Cum | 50 | 8000 | 400000 |  | 8000 | 0 | 0 | 0 |  | 0 | 0 | 0
| Sub-Total 2 |  |  |  | 640000 |  |  | 0 |  | 0 |  | 0 |  | 0
3 | Structural Works | [13 empty] | 0 | 0 |  | #REF!
3.1 | Excavation for Structures Foundation, Earth work in excavation of foundation of structures, including construction of shoring and bracing, removal of stumps and other deleterious matter & Backfilling with Suitable Material as per Drawing and Technical Specifications.,[907] | Cum | 443.18 | 50 | 22159 |  | 50 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | #REF!
3.2 | Providing and laying of hand pack Stone soling with 150 to 200 mm thick stones and packing with smaller stone on prepared surface as per Drawing and Technical Specifications.[1006] | Cum | 158.95 | 2200 | 349690 |  | 2200 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | #REF!
3.3 | Providing and laying of Plain Cement Concrete M 10 ( or 1:3:6 for nominal mix) in Foundation complete as per Drawing and Technical Specifications.[2000] | Cum | 2.16 | 6000 | 12960 |  | 6000 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | #REF!
3.4 | Providing and laying of Plain/Reinforced Cement Concrete in Foundation complete as per Drawing and Technical Specifications, PCC Grade M 15 including formworks all complete.[2000] | Cum | 22.62 | 7000 | 158340 |  | 7000 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | #REF!
3.5 | Providing and laying Plum concrete ( Boulder mixed concrete) as per Drawing and Specifications, 60% M 15 concrete and 40% boulders/stones,Including Formwork using Mechanical Aids[2421] | Cum | 423.26 | 6250 | 2645375 |  | 6250 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | #REF!
3.6 | Random Rubble Masonry, Providing and laying of Stone Masonry Work in Cement Mortar 1:4 in Foundation complete as per Drawing and Technical Specifications., Using Concrete Mixer[2602,2603] | Cum | 164.44 | 5000 | 822200 |  | 5000 | 0 | 0 | 0 |  | 0 | 0 | 0
3.7 | Providing, Assembling & providing and filling stone in mechanically woven double twisted crates / mattress including rolling, cutting and with lacing wire and binding wire as per specification , Hexagonal mesh type 100 mm x 120 mm, mesh wire 3 mm, selvage wire 3.9 mm, lacing wire 2.4 mm [SS 2402] | Cum | 97.5 | 3500 | 341250 |  | 3500 | 0 | 0 | 0 |  | 0 | 0 | 0
3.8 | Laying and fixing of Geo-Textile all complete as per specification., Providing and laying of a geotextile filter between pitching and embankment slopes as per Drawing and Technical Specifications.[2404] | Sqm | 57 | 70 | 3990 |  | 70 | 0 | 0 | 0 |  | 0 | 0 | 0
| Sub-Total 3 |  |  |  | 4355964 |  |  | 0 |  | 0 |  | 0 |  | 0
4 | Pavement Works | [6 empty] | 0 | [6 empty] | 0 | 0 |  | #REF!
4.1 | Providing and laying of Plain/Reinforced Cement Concrete in Foundation complete as per Drawing and Technical Specifications., RCC Grade M 25/20 including formwork [2000] | Cum | 92.12 | 8000 | 736960 |  | 8000 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | #REF!
4.2 | Providing and laying , fitting and placing un-coated Mild steel / HYSD reinforcement complete in foundation as per drawing and technical specification [2014] | Ton | 3.83 | 110000 | 421300 |  | 110000 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | #REF!
| Sub-Total 4 |  |  |  | 1158260 |  |  | 0 |  | 0 |  | 0 |  | 0
|  | Total with PS amount |  |  | 5675094 |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  | PS amount |  |  | 50000 |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  | Total without PS |  |  | 5625094 |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  | VAT 13% |  |  | 731262.22 |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  | Grand Total Inclusive VAT and PS |  |  | 6406356.22 |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0

## 1-1
a
b
c
d
e
f
Measurement Sheet
Name of Project:xx
Contract Identification No:- xx
Name of Contractor: xx
S.N. | Description of works | Unit | No. | Length (m) | Breadth (m) | Height (m) | Quantity | Remarks
1.1 | Relocation of services / minor infrastructures, Engineer's facility, Office accessories and equipments, Quality Control as per specifications and instruction of the Engineer.[111] | PS
|  |  |  | Total Quantity |  |  | 0
|  |  |  | Previous Bill Quantity |  |  | 0
|  |  |  | This Bill Quantity |  |  | 0

## 1-2
a
b
c
d
e
f
Measurement Sheet
Name of Project:xx
Contract Identification No:- xx
Name of Contractor: xx
S.N. | Description of works | Unit | No. | Length (m) | Breadth (m) | Height (m) | Quantity | Remarks
1.2 | Provision of Insurance for the loss or damage to the Works, Plant, and Materials; as per SCC 19.1 [SS 100] | Job
|  |  |  | Total Quantity |  |  | 0
|  |  |  | Previous Bill Quantity |  |  | 0
|  |  |  | This Bill Quantity |  |  | 0

## 2-1
a
b
c
d
e
f
Measurement Sheet
Name of Project:xx
Contract Identification No:- xx
Name of Contractor: xx
S.N. | Description of works | Unit | No. | Length (m) | Breadth (m) | Height (m) | Quantity | Remarks
2.1 | Road way Excavation in all types (including hard rock) of soil as per Drawing and technical specifications including removal of stumps and other deleterious matter, all lifts and lead as per Drawing and instruction of the Engineer[905] | Cum
|  |  |  | Total Quantity |  |  | 0
|  |  |  | Previous Bill Quantity |  |  | 0
|  |  |  | This Bill Quantity |  |  | 0

## 2-2
a
b
c
d
e
f
Measurement Sheet
Name of Project:xx
Contract Identification No:- xx
Name of Contractor: xx
S.N. | Description of works | Unit | No. | Length (m) | Breadth (m) | Height (m) | Quantity | Remarks
2.2 | Providing and laying of Plain/Reinforced Cement Concrete in Foundation complete as per Drawing and Technical Specifications, PCC Grade M 15 including formworks all complete.[2000] | Cum
|  |  |  | Total Quantity |  |  | 0
|  |  |  | Previous Bill Quantity |  |  | 0
|  |  |  | This Bill Quantity |  |  | 0

## 3-1
a
b
c
d
e
f
Measurement Sheet
Name of Project:xx
Contract Identification No:- xx
Name of Contractor: xx
S.N. | Description of works | Unit | No. | Length (m) | Breadth (m) | Height (m) | Quantity | Remarks
3.1 | Excavation for Structures Foundation, Earth work in excavation of foundation of structures, including construction of shoring and bracing, removal of stumps and other deleterious matter & Backfilling with Suitable Material as per Drawing and Technical Specifications.,[907] | Cum
|  |  |  | Total Quantity |  |  | 0
|  |  |  | Previous Bill Quantity |  |  | 0
|  |  |  | This Bill Quantity |  |  | 0

## 3-2
a
b
c
d
e
f
Measurement Sheet
Name of Project:xx
Contract Identification No:- xx
Name of Contractor: xx
S.N. | Description of works | Unit | No. | Length (m) | Breadth (m) | Height (m) | Quantity | Remarks
3.2 | Providing and laying of hand pack Stone soling with 150 to 200 mm thick stones and packing with smaller stone on prepared surface as per Drawing and Technical Specifications.[1006] | Cum
|  |  |  | Total Quantity |  |  | 0
|  |  |  | Previous Bill Quantity |  |  | 0
|  |  |  | This Bill Quantity |  |  | 0

## 3-3
a
b
c
d
e
f
Measurement Sheet
Name of Project:xx
Contract Identification No:- xx
Name of Contractor: xx
S.N. | Description of works | Unit | No. | Length (m) | Breadth (m) | Height (m) | Quantity | Remarks
3.3 | Providing and laying of Plain Cement Concrete M 10 ( or 1:3:6 for nominal mix) in Foundation complete as per Drawing and Technical Specifications.[2000] | Cum
|  |  |  | Total Quantity |  |  | 0
|  |  |  | Previous Bill Quantity |  |  | 0
|  |  |  | This Bill Quantity |  |  | 0

## 3-4
a
b
c
d
e
f
Measurement Sheet
Name of Project:xx
Contract Identification No:- xx
Name of Contractor: xx
S.N. | Description of works | Unit | No. | Length (m) | Breadth (m) | Height (m) | Quantity | Remarks
3.4 | Providing and laying of Plain/Reinforced Cement Concrete in Foundation complete as per Drawing and Technical Specifications, PCC Grade M 15 including formworks all complete.[2000] | Cum
|  |  |  | Total Quantity |  |  | 0
|  |  |  | Previous Bill Quantity |  |  | 0
|  |  |  | This Bill Quantity |  |  | 0

## 3-5
a
b
c
d
e
f
Measurement Sheet
Name of Project:xx
Contract Identification No:- xx
Name of Contractor: xx
S.N. | Description of works | Unit | No. | Length (m) | Breadth (m) | Height (m) | Quantity | Remarks
3.5 | Providing and laying Plum concrete ( Boulder mixed concrete) as per Drawing and Specifications, 60% M 15 concrete and 40% boulders/stones,Including Formwork using Mechanical Aids[2421] | Cum
|  |  |  | Total Quantity |  |  | 0
|  |  |  | Previous Bill Quantity |  |  | 0
|  |  |  | This Bill Quantity |  |  | 0

## 3-6
a
b
c
d
e
f
Measurement Sheet
Name of Project:xx
Contract Identification No:- xx
Name of Contractor: xx
S.N. | Description of works | Unit | No. | Length (m) | Breadth (m) | Height (m) | Quantity | Remarks
3.6 | Random Rubble Masonry, Providing and laying of Stone Masonry Work in Cement Mortar 1:4 in Foundation complete as per Drawing and Technical Specifications., Using Concrete Mixer[2602,2603] | Cum
|  |  |  | Total Quantity |  |  | 0
|  |  |  | Previous Bill Quantity |  |  | 0
|  |  |  | This Bill Quantity |  |  | 0

## 3-7
a
b
c
d
e
f
Measurement Sheet
Name of Project:xx
Contract Identification No:- xx
Name of Contractor: xx
S.N. | Description of works | Unit | No. | Length (m) | Breadth (m) | Height (m) | Quantity | Remarks
3.7 | Providing, Assembling & providing and filling stone in mechanically woven double twisted crates / mattress including rolling, cutting and with lacing wire and binding wire as per specification , Hexagonal mesh type 100 mm x 120 mm, mesh wire 3 mm, selvage wire 3.9 mm, lacing wire 2.4 mm [SS 2402] | Cum
|  |  |  | Total Quantity |  |  | 0
|  |  |  | Previous Bill Quantity |  |  | 0
|  |  |  | This Bill Quantity |  |  | 0

## 3-8
a
b
c
d
e
f
Measurement Sheet
Name of Project:xx
Contract Identification No:- xx
Name of Contractor: xx
S.N. | Description of works | Unit | No. | Length (m) | Breadth (m) | Height (m) | Quantity | Remarks
3.8 | Laying and fixing of Geo-Textile all complete as per specification., Providing and laying of a geotextile filter between pitching and embankment slopes as per Drawing and Technical Specifications.[2404] | Sqm
|  |  |  | Total Quantity |  |  | 0
|  |  |  | Previous Bill Quantity |  |  | 0
|  |  |  | This Bill Quantity |  |  | 0

## 4-1
a
b
c
d
e
f
Measurement Sheet
Name of Project:xx
Contract Identification No:- xx
Name of Contractor: xx
S.N. | Description of works | Unit | No. | Length (m) | Breadth (m) | Height (m) | Quantity | Remarks
4.1 | Providing and laying of Plain/Reinforced Cement Concrete in Foundation complete as per Drawing and Technical Specifications., RCC Grade M 25/20 including formwork [2000] | Cum
|  |  |  | Total Quantity |  |  | 0
|  |  |  | Previous Bill Quantity |  |  | 0
|  |  |  | This Bill Quantity |  |  | 0

## 4-2
a
b
c
d
e
f
Measurement Sheet
Name of Project:xx
Contract Identification No:- xx
Name of Contractor: xx
S.N. | Description of works | Unit | No. | Length (m) | Breadth (m) | Height (m) | Quantity | Remarks
4.2 | Providing and laying , fitting and placing un-coated Mild steel / HYSD reinforcement complete in foundation as per drawing and technical specification [2014] | Ton
|  |  |  | Total Quantity |  |  | 0
|  |  |  | Previous Bill Quantity |  |  | 0
|  |  |  | This Bill Quantity |  |  | 0